## Testing functionality - issues
Superadmin
Reactivate Business Not working
Overview - West Bridgford Plumbing not showing as recent
Suser creation - only for Admin and Super Admin
Plans and Pricing Not showinh
Lookup Values - should these be Super Admin?
All users are visible, should these just be admin users?
Users - Filters don’t always work.
Admin Mode
Tradesperson Mode
Dashboard Books are =0
Only Tradesperson can add a booking but can't add a new TP
Invite Link not working - Fix?
Calendar Not whowing correctly
Job Types - can only select Job if approved by Admin
Created an accound - did a boking and it disappeared
General
Split Quote & Job Booking
Archive Timeframe - 30 days
Team Jobs
Pricing
Payments
Do we want to offer payment for Individual TP?
Messages and communication Log - tracking of all messages and appointments - receipt of accepted appointment. Or confirmation response to text / whatsapp.
Austomated update to PAID status on receipt of payment - how does this work with Invoicing?
Russell Feedback
It would be useful if each booking had a field which was quote or job and this could be one of the categories across the top that could be selected to show all quotes etc. (currently shows pending, completed etc).
There is no status for invoiced (assume this was under the trades person role but I am both under this id).
In the view of jobs can you show address to the right of the name - I had 2 neils so had to put address in their name.
I presume the orange confirm button (and notify customer does not work yet - it showed an error message)
Ideally I would note all these things down and do it in one go but sometimes it's easier to just get it down and you can think about the issues later if necessary. Had a quick look through the scoping document - which is useful but thought I would note down the stages
a) quote details
b) schedule
c) price quote and communicate
d) quote accepted
e) quote now a pending job
f) schedule job
g) delay job
h) complete job
I) invoice job
j) invoice paid
k) issue certificate and request for feedback
Sometimes we may miss stages out but somehow we need have all of those stages and means to filter or show the different stages/stages
Ok - just to let you know I haven't seen or used anything to do with sending estimates/quotes (or invoicing). One idea I did have was that once payment is received you could send a link asking for a Google review.
What I realized was that for something I didn't know a date for ie future date I could just put today's date and then go back to it. But whether there is a filter to show bookings with no date, past dates, current or future???

## TODO
ID | PRIORITY | AREA | TITLE | STATUS | ALLOCATED TO | TARGET DATE | NOTES
1 | HIGH | Landing page | Site marketing landing page | Idea |  | 2026-04-17 | Create a landing page for the site that explains the core benefits of the app and who can use it, what the subscriptions are and what you get for your money. Should be outcome and benefit focused.
2 | HIGH | Job management | End to end process flow | In Progress | Matt | 2026-04-10 | Build in the concept of a process flow from job creation and quoting through delivery, completion and invoice.
3 | HIGH | Bug fixing | Russell initial feedback bug fixing | In Progress | Matt | 2026-04-10 | See feedback from "Testing functionality - issues" tab.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30